## agile_sports_project
Issue_Type | title | Issue_Parent | Description_No_Actions | due_date | label | label | assign | assignee | blocks | state | relation | description
Epic | FrontEnd | NA | The FrontEnd epic involves building the user interface for the application, enabling users to interact with game data, player statistics, and live notifications. This interface will support functionalities such as a user dashboard to display real-time game statistics, a data visualization section for player and team performance metrics, a login and authentication system for secure access (if time allows only), and a notification system to inform users of real-time updates. User Dashboard: Design a dashboard to present real-time game statistics, player performance metrics, and relevant recommendations. The dashboard will include structured sections for game stats, player information, and data insights. Data updates will be automatically integrated from the backend's live data feed. Player and Team Data Visualization: Create visual components to allow users to view and analyze player and team performance metrics. Implement dynamic graphs and charts to visualize metrics like speed and stress levels, as well as a team statistics overview for collective performance data. User Login and Authentication: Develop a secure login system to manage user access and roles. Role-based access control will enable differentiated access for admins, coaches, and players. The authentication flow will include login only. (If time permits) Real-Time Notifications: Implement a system to provide users with real-time notifications, including player status updates and event alerts. The notification system will be connected to the backend through WebSocket to push immediate updates. | 2024-12-01 | /label | EPIC | [5 empty] | The FrontEnd epic involves building the user interface for the application, enabling users to interact with game data, player statistics, and live notifications. This interface will support functionalities such as a user dashboard to display real-time game statistics, a data visualization section for player and team performance metrics, a login and authentication system for secure access (if time allows only), and a notification system to inform users of real-time updates. User Dashboard: Design a dashboard to present real-time game statistics, player performance metrics, and relevant recommendations. The dashboard will include structured sections for game stats, player information, and data insights. Data updates will be automatically integrated from the backend's live data feed. Player and Team Data Visualization: Create visual components to allow users to view and analyze player and team performance metrics. Implement dynamic graphs and charts to visualize metrics like speed and stress levels, as well as a team statistics overview for collective performance data. User Login and Authentication: Develop a secure login system to manage user access and roles. Role-based access control will enable differentiated access for admins, coaches, and players. The authentication flow will include login only. (If time permits) Real-Time Notifications: Implement a system to provide users with real-time notifications, including player status updates and event alerts. The notification system will be connected to the backend through WebSocket to push immediate updates. /label EPIC | 1 |  |  |  | 184 |  | Design the layout for the dashboard to display real-time stats, player data, and recommendations. /label SUBTASK /assign @s2610072 /blocks #2
Feature | User Dashboard | FrontEnd | Create a user-facing dashboard to display game and player statistics. |  | /label | FEATURE | /assign | @s2610072 | /blocks #184 |  | /relate #184 | Create a user-facing dashboard to display game and player statistics. /label FEATURE /assign @s2610072 /blocks #184 /relate #184 | 2 | @s2276643 | @s2610072 | @s2760468 | 185 | me @s2276643 @s2610072 @s2760468
Story | Create Dashboard Layout | User Dashboard | Design the layout for the dashboard to display real-time stats, player data, and recommendations. |  | /label | SUBTASK | /assign | @s2610072 | /blocks #185 |  | /relate #185 | Design the layout for the dashboard to display real-time stats, player data, and recommendations. /label SUBTASK /assign @s2610072 /blocks #185 /relate #185 | 3 |  |  |  | 186
Subtask | Wireframe Dashboard | Create Dashboard Layout | Design wireframes for the dashboard, showing player data, game stats, and recommended actions. |  | /label | SUBTASK | /assign | @s2610072 |  |  | /relate #186 | Design wireframes for the dashboard, showing player data, game stats, and recommended actions. /label SUBTASK /assign @s2610072 /relate #186 | 4 |  |  |  | 187
Subtask | Develop UI Components | Create Dashboard Layout | Build reusable UI components such as cards, graphs, and stat tables for the dashboard. |  | /label | SUBTASK | /assign | @s2610072 |  |  | /relate #186 | Build reusable UI components such as cards, graphs, and stat tables for the dashboard. /label SUBTASK /assign @s2610072 /relate #186 | 5 | @s2276643 | Alyssa |  | 188
Subtask | Integrate Live Data Feed | Create Dashboard Layout | Connect the UI to the backend's live data feed for real-time statistics. |  | /label | SUBTASK | /assign | @s2610072 |  |  | /relate #186 | Connect the UI to the backend's live data feed for real-time statistics. /label SUBTASK /assign @s2610072 /relate #186 | 6 | @s2610072 | Lara Ann |  | 189
Story | Player and Team Data Visualization | User Dashboard | Visualize player and team performance metrics using charts and graphs. |  | /label | STORY | /assign | @s2610072 | /blocks #185 |  | /relate #185 | Visualize player and team performance metrics using charts and graphs. /label STORY /assign @s2610072 /blocks #185 /relate #185 | 7 | @s2760468 | Konstantinos |  | 190
Subtask | Design Player Data Visuals | Player and Team Data Visualization | Create dynamic charts to display player performance metrics like speed, stress levels, etc. |  | /label | SUBTASK | /assign | @s2610072 |  |  | /relate #190 | Create dynamic charts to display player performance metrics like speed, stress levels, etc. /label SUBTASK /assign @s2610072 /relate #190 | 8 |  |  |  | 191
Subtask | Team Statistics Overview | Player and Team Data Visualization | Develop a team overview page showing collective performance metrics for the team. |  | /label | SUBTASK | /assign | @s2610072 |  |  | /relate #190 | Develop a team overview page showing collective performance metrics for the team. /label SUBTASK /assign @s2610072 /relate #190 | 9 |  |  |  | 192
Subtask | Implement Filtering and Sorting | Player and Team Data Visualization | Enable filtering by date, player, and metrics to view specific data trends. |  | /label | SUBTASK | /assign | @s2610072 |  |  | /relate #190 | Enable filtering by date, player, and metrics to view specific data trends. /label SUBTASK /assign @s2610072 /relate #190 | 10 |  |  |  | 193
Story | User Login and Authentication | User Dashboard | Implement user authentication for access to personalized data and settings. |  | /label | STORY | /assign | @s2610072 | /blocks #185 |  | /relate #185 | Implement user authentication for access to personalized data and settings. /label STORY /assign @s2610072 /blocks #185 /relate #185 | 11 |  |  |  | 194
Subtask | Design Login Page | User Login and Authentication | Create a UI for user login, registration, and password recovery. |  | /label | SUBTASK | /assign | @s2610072 |  |  | /relate #194 | Create a UI for user login, registration, and password recovery. /label SUBTASK /assign @s2610072 /relate #194 | 12 |  |  |  | 195
Subtask | Implement Authentication API | User Login and Authentication | Connect frontend to authentication backend to validate users and manage sessions. |  | /label | SUBTASK | /assign | @s2610072 |  |  | /relate #194 | Connect frontend to authentication backend to validate users and manage sessions. /label SUBTASK /assign @s2610072 /relate #194 | 13 |  |  |  | 196
Subtask | Build Role-based Access Control | User Login and Authentication | Implement access control for different user types, including admins, coaches, and players. |  | /label | SUBTASK | /assign | @s2610072 |  |  | /relate #194 | Implement access control for different user types, including admins, coaches, and players. /label SUBTASK /assign @s2610072 /relate #194 | 14 |  |  |  | 197
Feature | Real-Time Notifications | FrontEnd | Notify users with live updates on player status, game events, and performance alerts. |  | /label | FEATURE | /assign | @s2610072 | /blocks #184 |  | /relate #184 | Notify users with live updates on player status, game events, and performance alerts. /label FEATURE /assign @s2610072 /blocks #184 /relate #184 | 15 |  |  |  | 198
Story | Build Notification System | Real-Time Notifications | Develop a system to show real-time notifications for events such as injuries or performance alerts. |  | /label | STORY | /assign | @s2610072 | /blocks #199 |  | /relate #198 | Develop a system to show real-time notifications for events such as injuries or performance alerts. /label STORY /assign @s2610072 /blocks #199 /relate #198 | 16 |  |  |  | 199
Subtask | Design Notification UI | Build Notification System | Create a UI for in-app notifications and alerts. |  | /label | SUBTASK | /assign | @s2610072 |  |  | /relate #198 | Create a UI for in-app notifications and alerts. /label SUBTASK /assign @s2610072 /relate #198 | 17 |  |  |  | 200
Subtask | Connect WebSocket for Live Notifications | Build Notification System | Integrate WebSockets to display live notifications from the backend. |  | /label | SUBTASK | /assign | @s2610072 |  |  | /relate #198 | Integrate WebSockets to display live notifications from the backend. /label SUBTASK /assign @s2610072 /relate #198 | 18 |  |  |  | 201
Subtask | Implement Notification Preferences | Build Notification System | Allow users to customize the type of notifications they want to receive. |  | /label | SUBTASK | /assign | @s2610072 |  |  | /relate #198 | Allow users to customize the type of notifications they want to receive. /label SUBTASK /assign @s2610072 /relate #198 | 19 |  |  |  | 202
Epic | BackEnd | NA | The BackEnd epic focuses on the core infrastructure and data processing services that enable data ingestion, real-time analytics, and storage. Key components include setting up Kafka for data streaming, Spark for real-time data processing, and HDFS for long-term storage. The backend handles high-frequency data ingestion, validation, and analysis from devices that monitor player stats and game data. The backend is designed to be scalable and supports API endpoints that the frontend can access to retrieve both real-time and historical data. Project Setup: Establish the foundational structure of the backend, including folder organization, configuration, and dependency installation. Ensure consistency across components like API, Spark, and Docker for streamlined development and deployment. Kafka Setup: Configure Kafka as the message broker for ingesting and processing streaming data. Kafka topics will be used to separate data by device and session. Spark Setup: Set up Apache Spark to process data streams in real time from Kafka topics. Spark will perform data transformations, aggregations, and compute metrics like average and max values in real time, making it possible to generate insights as data is received. Data Ingestion: Develop APIs and data pipelines to ingest data from monitoring devices. The backend will validate incoming data against predefined schemas. Data is stored in a structured format, ready for real-time or batch analysis. Performance Analysis and Recommendations: Analyze player data to identify performance trends and generate recommendations. Integrate machine learning models within Spark to predict outcomes and suggest performance improvements. Injury prevention recommendations will be generated based on real-time and historical data. Application Testing: Implement testing using Mockaroo for synthetic data generation and Postman for API testing. This ensures that the backend services handle data ingestion, processing, and retrieval accurately and reliably. | 2024-12-01 | /label | EPIC |  |  | /blocks #184 |  | /relate #184 | The BackEnd epic focuses on the core infrastructure and data processing services that enable data ingestion, real-time analytics, and storage. Key components include setting up Kafka for data streaming, Spark for real-time data processing, and HDFS for long-term storage. The backend handles high-frequency data ingestion, validation, and analysis from devices that monitor player stats and game data. The backend is designed to be scalable and supports API endpoints that the frontend can access to retrieve both real-time and historical data. Project Setup: Establish the foundational structure of the backend, including folder organization, configuration, and dependency installation. Ensure consistency across components like API, Spark, and Docker for streamlined development and deployment. Kafka Setup: Configure Kafka as the message broker for ingesting and processing streaming data. Kafka topics will be used to separate data by device and session. Spark Setup: Set up Apache Spark to process data streams in real time from Kafka topics. Spark will perform data transformations, aggregations, and compute metrics like average and max values in real time, making it possible to generate insights as data is received. Data Ingestion: Develop APIs and data pipelines to ingest data from monitoring devices. The backend will validate incoming data against predefined schemas. Data is stored in a structured format, ready for real-time or batch analysis. Performance Analysis and Recommendations: Analyze player data to identify performance trends and generate recommendations. Integrate machine learning models within Spark to predict outcomes and suggest performance improvements. Injury prevention recommendations will be generated based on real-time and historical data. Application Testing: Implement testing using Mockaroo for synthetic data generation and Postman for API testing. This ensures that the backend services handle data ingestion, processing, and retrieval accurately and reliably. /label EPIC /blocks #184 /relate #184 | 20 |  |  |  | 203
Feature | Project Setup | BackEnd | Setup the overall project structure and configurations. | 2024-10-21 | /label | FEATURE | /assign | me @s2276643 @s2760468 | /blocks #203 | /done | /relate #203 | Setup the overall project structure and configurations. /label FEATURE /assign me @s2276643 @s2760468 /blocks #203 /done /relate #203 | 21 |  |  |  | 204
Story | Organize Project Structure | Project Setup | Organize folders and necessary files for API, Spark, and Docker. | 2024-10-15 | /label | STORY | /assign | me @s2276643 @s2760468 |  | /done | /relate #204 | Organize folders and necessary files for API, Spark, and Docker. /label STORY /assign me @s2276643 @s2760468 /done /relate #204 | 22 |  |  |  | 205
Subtask | Create Project Folders and Files | Organize Project Structure | Organize folders for API, Spark processing, config, and Docker. | 2024-10-10 | /label | SUBTASK | /assign | me @s2276643 @s2760468 |  | /done | /relate #205 | Organize folders for API, Spark processing, config, and Docker. /label SUBTASK /assign me @s2276643 @s2760468 /done /relate #205 | 23 |  |  |  | 206
Subtask | Add Configuration Files | Organize Project Structure | Add necessary config files (e.g., config.py for API and Spark). | 2024-10-12 | /label | SUBTASK | /assign | me @s2276643 @s2760468 |  | /done | /relate #205 | Add necessary config files (e.g., config.py for API and Spark). /label SUBTASK /assign me @s2276643 @s2760468 /done /relate #205 | 24 |  |  |  | 207
Subtask | Setup Virtual Environment | Organize Project Structure | Setup virtual environment and install dependencies (FastAPI, Kafka, Spark). | 2024-10-13 | /label | SUBTASK | /assign | me @s2276643 @s2760468 |  | /done | /relate #205 | Setup virtual environment and install dependencies (FastAPI, Kafka, Spark). /label SUBTASK /assign me @s2276643 @s2760468 /done /relate #205 | 25 |  |  |  | 208
Subtask | Create `.gitignore` and README | Organize Project Structure | Define `.gitignore` and add README with project instructions. | 2024-10-15 | /label | SUBTASK | /assign | me @s2276643 @s2760468 |  | /done | /relate #205 | Define `.gitignore` and add README with project instructions. /label SUBTASK /assign me @s2276643 @s2760468 /done /relate #205 | 26 |  |  |  | 209
Feature | Kafka Setup | BackEnd | Set up Kafka as a message broker for data ingestion. | 2024-11-20 | /label | FEATURE | /assign | me | /blocks #203 | /done | /relate #203 | Set up Kafka as a message broker for data ingestion. /label FEATURE /assign me /blocks #203 /done /relate #203 | 27 |  |  |  | 210
Story | Install and Configure Kafka | Kafka Setup | Set up Kafka services using Docker and integrate with the API. | 2024-11-20 | /label | STORY | /assign | me | /blocks #210 | /done | /relate #210 | Set up Kafka services using Docker and integrate with the API. /label STORY /assign me /blocks #210 /done /relate #210 | 28 |  |  |  | 211
Subtask | Add Docker Service for Kafka | Install and Configure Kafka | Add Kafka service in docker-compose.yml and configure it with Zookeeper. | 2024-11-15 | /label | SUBTASK | /assign | me |  | /done | /relate #211 | Add Kafka service in docker-compose.yml and configure it with Zookeeper. /label SUBTASK /assign me /done /relate #211 | 29 |  |  |  | 212
Subtask | Configure Kafka Producer in API | Install and Configure Kafka | Configure a Kafka producer in FastAPI to stream data. | 2024-10-30 | /label | SUBTASK | /assign | me |  | /done | /relate #211 | Configure a Kafka producer in FastAPI to stream data. /label SUBTASK /assign me /done /relate #211 | 30 |  |  |  | 213
Subtask | Configure Kafka Consumer for Spark | Install and Configure Kafka | Set up Kafka consumer logic in Spark for real-time data ingestion. | 2024-11-02 | /label | SUBTASK | /assign | me |  | /done | /relate #211 | Set up Kafka consumer logic in Spark for real-time data ingestion. /label SUBTASK /assign me /done /relate #211 | 31 |  |  |  | 214
Feature | Spark Setup | BackEnd | Set up Apache Spark for real-time data processing using Kafka. | 2024-11-20 | /label | FEATURE | /assign | me | /blocks #203 | /done | /relate #203 | Set up Apache Spark for real-time data processing using Kafka. /label FEATURE /assign me /blocks #203 /done /relate #203 | 32 |  |  |  | 215
Story | Install and Configure Apache Spark | Spark Setup | Configure Apache Spark with Kafka for real-time streaming. | 2024-11-02 | /label | STORY | /assign | me | /blocks #215 | /done | /relate #215 | Configure Apache Spark with Kafka for real-time streaming. /label STORY /assign me /blocks #215 /done /relate #215 | 33 |  |  |  | 216
Subtask | Add Docker Service for Spark | Install and Configure Apache Spark | Configure a Spark service in docker-compose.yml. | 2024-11-05 | /label | SUBTASK | /assign | me |  | /done | /relate #216 | Configure a Spark service in docker-compose.yml. /label SUBTASK /assign me /done /relate #216 | 34 |  |  |  | 217
Subtask | Set Up Spark Dependencies | Install and Configure Apache Spark | Install and set up dependencies for Spark in Dockerfile. | 2024-11-05 | /label | SUBTASK | /assign | me |  | /done | /relate #216 | Install and set up dependencies for Spark in Dockerfile. /label SUBTASK /assign me /done /relate #216 | 35 |  |  |  | 218
Subtask | Implement Spark Streaming | Install and Configure Apache Spark | Set up Spark Structured Streaming to consume Kafka data. | 2024-11-15 | /label | SUBTASK | /assign | me |  | /done | /relate #216 | Set up Spark Structured Streaming to consume Kafka data. /label SUBTASK /assign me /done /relate #216 | 36 |  |  |  | 219
Feature | Data Ingestion | BackEnd | Ingest and process data from recording devices, games, and player stats. | 2024-10-30 | /label | FEATURE | /assign | me | /blocks #203 | /done | /relate #203 | Ingest and process data from recording devices, games, and player stats. /label FEATURE /assign me /blocks #203 /done /relate #203 | 37 |  |  |  | 220
Story | Device Data Interface | Data Ingestion | Create an interface to capture data from recording devices monitoring player movements and stress using Kafka. | 2024-10-10 | /label | STORY | /assign | me | /blocks #219 | /done | /relate #220 | Create an interface to capture data from recording devices monitoring player movements and stress using Kafka. /label STORY /assign me /blocks #219 /done /relate #220 | 38 |  |  |  | 221
Subtask | Setup Device APIs | Device Data Interface | Develop APIs to ingest data from multiple recording devices. | 2024-10-08 | /label | SUBTASK | /assign | me |  | /done | /relate #221 | Develop APIs to ingest data from multiple recording devices. /label SUBTASK /assign me /done /relate #221 | 39 |  |  |  | 222
Subtask | Data Validation and Cleaning | Device Data Interface | Implement validation and cleaning of incoming device data to ensure accuracy. | 2024-10-05 | /label | SUBTASK | /assign | me |  | /done | /relate #221 | Implement validation and cleaning of incoming device data to ensure accuracy. /label SUBTASK /assign me /done /relate #221 | 40 |  |  |  | 223
Subtask | Store Data in Database | Device Data Interface | Develop logic to store device data in a structured format in the database. | 2024-10-01 | /label | SUBTASK | /assign | me |  | /done | /relate #221 | Develop logic to store device data in a structured format in the database. /label SUBTASK /assign me /done /relate #221 | 41 |  |  |  | 224
Story | Game Stats Ingestion | Data Ingestion | Build a system to gather game and player stats for analysis. | 2024-10-30 | /label | STORY | /assign | me | /blocks #220 | /done | /relate #220 | Build a system to gather game and player stats for analysis. /label STORY /assign me /blocks #220 /done /relate #220 | 42 |  |  |  | 225
Subtask | Develop Game Stats API | Game Stats Ingestion | Create APIs to gather and ingest statistics from games and players. | 2024-10-28 | /label | SUBTASK | /assign | me |  | /done | /relate #225 | Create APIs to gather and ingest statistics from games and players. /label SUBTASK /assign me /done /relate #225 | 43 |  |  |  | 226
Subtask | Database Design for Stats | Game Stats Ingestion | Design a database schema to store game and player statistics for analysis. | 2024-10-25 | /label | SUBTASK | /assign | me |  | /done | /relate #225 | Design a database schema to store game and player statistics for analysis. /label SUBTASK /assign me /done /relate #225 | 44 |  |  |  | 227
Subtask | Implement Batch Processing | Game Stats Ingestion | Develop a batch processing system to handle large volumes of stats data. | 2024-10-22 | /label | SUBTASK | /assign | me |  | /done | /relate #225 | Develop a batch processing system to handle large volumes of stats data. /label SUBTASK /assign me /done /relate #225 | 45 |  |  |  | 228
Feature | Performance Analysis and Recommendations | BackEnd | Analyze player data to identify improvements and generate training/injury recommendations. |  | /label | FEATURE | /assign | @s2760468 | /blocks #203 |  | /relate #203 | Analyze player data to identify improvements and generate training/injury recommendations. /label FEATURE /assign @s2760468 /blocks #203 /relate #203 | 46 |  |  |  | 229
Story | Build Performance Metrics Analyzer | Performance Analysis and Recommendations | Analyze player stats and device data to identify performance metrics. |  | /label | STORY | /assign | @s2760468 | /blocks #229 |  | /relate #229 | Analyze player stats and device data to identify performance metrics. /label STORY /assign @s2760468 /blocks #229 /relate #229 | 47 |  |  |  | 230
Subtask | Implement Data Analysis Logic | Build Performance Metrics Analyzer | Develop the backend logic to analyze stress, speed, and other performance metrics. |  | /label | SUBTASK | /assign | @s2760468 |  |  | /relate #230 | Develop the backend logic to analyze stress, speed, and other performance metrics. /label SUBTASK /assign @s2760468 /relate #230 | 48 |  |  |  | 231
Subtask | Integrate with Machine Learning Models | Build Performance Metrics Analyzer | Connect data analysis with machine learning models to detect trends and predict outcomes. |  | /label | SUBTASK | /assign | @s2760468 |  |  | /relate #230 | Connect data analysis with machine learning models to detect trends and predict outcomes. /label SUBTASK /assign @s2760468 /relate #230 | 49 |  |  |  | 232
Subtask | Store and Serve Analysis Results | Build Performance Metrics Analyzer | Store analysis results in the database and make them accessible via APIs. |  | /label | SUBTASK | /assign | @s2760468 |  |  | /relate #230 | Store analysis results in the database and make them accessible via APIs. /label SUBTASK /assign @s2760468 /relate #230 | 50 |  |  |  | 233
Story | Generate Injury Prevention Recommendations | Performance Analysis and Recommendations | Provide injury prevention tips based on analyzed player performance data. |  | /label | STORY | /assign | @s2760468 | /blocks #229 |  | /relate #229 | Provide injury prevention tips based on analyzed player performance data. /label STORY /assign @s2760468 /blocks #229 /relate #229 | 51 |  |  |  | 234
Subtask | Define Injury Risk Factors | Generate Injury Prevention Recommendations | Use data to identify risk factors for injuries in players. |  | /label | SUBTASK | /assign | @s2760468 |  |  | /relate #234 | Use data to identify risk factors for injuries in players. /label SUBTASK /assign @s2760468 /relate #234 | 52 |  |  |  | 235
Subtask | Build Recommendation Engine | Generate Injury Prevention Recommendations | Develop an engine to generate recommendations based on risk factors and performance data. |  | /label | SUBTASK | /assign | @s2760468 |  |  | /relate #234 | Develop an engine to generate recommendations based on risk factors and performance data. /label SUBTASK /assign @s2760468 /relate #234 | 53 |  |  |  | 236
Subtask | Create Recommendation API | Generate Injury Prevention Recommendations | Develop an API to serve injury prevention recommendations to the frontend. |  | /label | SUBTASK | /assign | @s2760468 |  |  | /relate #234 | Develop an API to serve injury prevention recommendations to the frontend. /label SUBTASK /assign @s2760468 /relate #234 | 54 |  |  |  | 237
Feature | Application Testing | BackEnd | Provide service to generate synthetic data, send to API, and test correct system workings. |  | /label | FEATURE | /assign | @s2276643 | /blocks #203 |  | /relate #203 | Provide service to generate synthetic data, send to API, and test correct system workings. /label FEATURE /assign @s2276643 /blocks #203 /relate #203 | 55 |  |  |  | 238
Story | Generate Synthetic Data with Mockaroo | Application Testing | Create synthetic test data using Mockaroo to simulate real-time sensor data for testing API and data pipelines. |  | /label | STORY | /assign | @s2276643 | /blocks #238 |  | /relate #238 | Create synthetic test data using Mockaroo to simulate real-time sensor data for testing API and data pipelines. /label STORY /assign @s2276643 /blocks #238 /relate #238 | 56 |  |  |  | 239
Subtask | Define Data Schema in Mockaroo | Generate Synthetic Data with Mockaroo | Set up a data schema in Mockaroo matching the API's expected device schema. |  | /label | SUBTASK | /assign | @s2276643 |  |  | /relate #239 | Set up a data schema in Mockaroo matching the API's expected device schema. /label SUBTASK /assign @s2276643 /relate #239 | 57 |  |  |  | 240
Subtask | Generate Sample Data Files | Generate Synthetic Data with Mockaroo | Use the schema in Mockaroo to generate sample data files for testing. |  | /label | SUBTASK | /assign | @s2276643 |  |  | /relate #239 | Use the schema in Mockaroo to generate sample data files for testing. /label SUBTASK /assign @s2276643 /relate #239 | 58 |  |  |  | 241
Story | API Testing with Postman | Application Testing | Use Postman to automate tests on API endpoints, checking for correct data validation, ingestion, and error handling. |  | /label | STORY | /assign | @s2276643 | /blocks #238 |  | /relate #238 | Use Postman to automate tests on API endpoints, checking for correct data validation, ingestion, and error handling. /label STORY /assign @s2276643 /blocks #238 /relate #238 | 59 |  |  |  | 242
Subtask | Create Postman Collection for API Endpoints | API Testing with Postman | Define a Postman collection with requests for each API endpoint, including device registration and data streaming. |  | /label | SUBTASK | /assign | @s2276643 |  |  | /relate #242 | Define a Postman collection with requests for each API endpoint, including device registration and data streaming. /label SUBTASK /assign @s2276643 /relate #242 | 60 |  |  |  | 243
Subtask | Run Automated Tests for Data Validation | API Testing with Postman | Set up and run automated tests in Postman to validate data sent to the API and handle expected responses. |  | /label | SUBTASK | /assign | @s2276643 |  |  | /relate #242 | Set up and run automated tests in Postman to validate data sent to the API and handle expected responses. /label SUBTASK /assign @s2276643 /relate #242 | 61 |  |  |  | 244

## Hoja1
label
EPIC
FEATURE
SUBTASK
SUBTASK
SUBTASK
SUBTASK
STORY
SUBTASK
SUBTASK
SUBTASK
STORY
SUBTASK
SUBTASK
SUBTASK
FEATURE
STORY
SUBTASK
SUBTASK
SUBTASK
FEATURE
SUBTASK
SUBTASK
SUBTASK
SUBTASK
FEATURE
STORY
SUBTASK
SUBTASK
SUBTASK
FEATURE
STORY
SUBTASK
SUBTASK
SUBTASK
FEATURE
STORY
SUBTASK
SUBTASK
SUBTASK
STORY
SUBTASK
SUBTASK
SUBTASK
FEATURE
STORY
SUBTASK
SUBTASK
SUBTASK
STORY
SUBTASK
SUBTASK
SUBTASK
FEATURE
STORY
SUBTASK
SUBTASK
STORY
SUBTASK
SUBTASK